## TemplateDoHistorico - Model Nam
Model Name and Version - Agent Name - Skills and Agents
Prompt | Issues | Overall result | Overall sentiment | Observations
# Implementer Prompt - Iteration 01 Implement only the first backend slice for student management. Project context: - Node + TypeScript backend - JSON persistence - current server already boots successfully - keep changes small and localized Required scope for this iteration: - create a modular student backend slice - implement GET /api/students - implement POST /api/students - persist students in a JSON file under the data directory - validate required fields: name, cpf, email - return clear HTTP responses for invalid input Constraints: - do not implement update or delete - do not touch frontend - do not implement classes, assessments, or notifications - do not refactor unrelated files - do not place all logic in route files Expected response format: 1. Objective 2. Files to change 3. Out of scope 4. Implementation summary 5. Manual validation steps 6. Risks or caveats | The implementation worked functionally, but the validation layer initially had semantic issues in its error modeling. A payload-level validation error was modeled as a field-level error, and the validator also included an artificial fallback branch mainly for TypeScript narrowing rather than domain clarity. A small manual adjustment was necessary. | Accepted with manual adjustment | Useful for a small backend slice with clear scope, but still required close review for semantic quality and clean validation design. | The agent respected the requested scope and produced a reasonably modular result with routing, validation, repository logic, and JSON persistence separated. Manual validation confirmed that GET and POST worked correctly and that invalid payloads were rejected. The main quality issue was not functionality, but the design of the validation response shape. This should be constrained more explicitly in future prompts.
# Implementer Prompt - Iteration 02 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-02/00-iteration-brief.md - sistema/docs/iterations/iteration-02/01-planner-output.md - sistema/server/src/routes/index.ts - sistema/server/src/modules/students/index.ts - sistema/server/src/modules/students/student.repository.ts - sistema/server/src/modules/students/student.validation.ts - sistema/server/src/shared/types/domain.ts Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly, but the first validation attempt was temporarily confused by pre-existing duplicated records already present in students.json. The duplicate-check logic worked correctly on a clean dataset, but the iteration depended on cleaning legacy duplicated test data before update validation could be interpreted correctly. | Accepted | Good result for a medium-sized backend slice. The agent respected scope, improved modularity with a service layer, and implemented the required HTTP behaviors with less manual adjustment than in Iteration 01. | The agent handled this iteration better than the previous one because the prompt required planning first and explicitly encouraged a service layer when the module grew. Duplicate checks and update rules were centralized more cleanly. The main caveat was not code failure, but confusion caused by previously duplicated test records in the JSON file. Future prompts should continue to enforce thin routes, shared validation, and centralized conflict logic.
# Implementer Prompt - Iteration 03 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-03/00-iteration-brief.md - sistema/docs/iterations/iteration-03/01-planner-output.md - sistema/server/src/routes/index.ts - sistema/server/src/modules/students/index.ts - sistema/server/src/modules/students/student.repository.ts - sistema/server/src/modules/students/student.service.ts - sistema/server/src/modules/students/student.validation.ts - sistema/server/src/shared/types/domain.ts Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly and required no meaningful manual code correction after generation. The main remaining concerns are architectural rather than functional: repository path handling still relies on process.cwd(), and JSON-file persistence remains simple and non-transactional. | Accepted | Good result for a focused backend slice. The agent respected the scope, preserved modularity, and extended the students backend cleanly without introducing unnecessary changes. | This iteration went more smoothly than the earlier ones because the prompt constrained the change set tightly and the students module already had a service/repository structure to extend. The delete behavior was implemented cleanly with correct status codes and correct persistence updates. The next prompts should continue using the same discipline of thin routes and localized changes.
# Implementer Prompt - Iteration 04 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-04/00-iteration-brief.md - sistema/docs/iterations/iteration-04/01-planner-output.md - sistema/server/package.json - sistema/server/src/modules/students/index.ts - sistema/server/src/modules/students/student.service.ts - sistema/server/src/modules/students/student.repository.ts - sistema/server/data/students.json Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly and did not require backend business-logic changes, but the test layer depends on a separately running local API and still inherits the simplicity of JSON-file state management. The suite also emits a Node-version warning in this environment, although execution succeeds. | Accepted | Good result for a test-infrastructure iteration. The agent respected scope, kept the setup simple, and created readable acceptance scenarios with a practical reset strategy. | This iteration was successful because the prompts constrained the solution to minimal Cucumber infrastructure and discouraged unnecessary complexity. The use of JavaScript step definitions and deterministic reset hooks kept the setup understandable. The main lesson is that stable acceptance tests for JSON-backed systems require explicit state control.
# Implementer Prompt - Iteration 05 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-05/00-iteration-brief.md - sistema/docs/iterations/iteration-05/01-planner-output.md - sistema/client/src/pages/StudentsPage.tsx - sistema/client/src/config/api.ts - sistema/client/src/types/domain.ts - sistema/client/src/router.tsx - sistema/client/src/styles.css Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The first students frontend slice worked well and looked good, but manual review found two follow-up UX issues: long student values could still stress the list layout, and CPF input was still too permissive in the UI. These issues are better handled in a dedicated corrective frontend-hardening iteration. | Accepted | Good result for a first frontend slice. The agent delivered a clearly improved and functional students page with clean visual organization, but a small corrective pass is still needed for stronger UX resilience. | The agent handled the visual requirement reasonably well once the prompt explicitly required a polished result. The best outcome came from combining functional scope with aesthetic constraints in the prompt. Manual review remains essential because overflow and input-hardening issues were only visible after real interaction with the page.
# Implementer Prompt - Iteration 06 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-06/00-iteration-brief.md - sistema/docs/iterations/iteration-06/01-planner-output.md - sistema/client/src/pages/StudentsPage.tsx - sistema/client/src/config/studentsApi.ts - sistema/client/src/styles.css Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly and solved the immediate frontend UX issues, but CPF validation is still enforced only in the frontend. This means invalid CPF values could still be sent directly to the backend API outside the UI, so a backend hardening follow-up is still necessary. | Accepted | Good corrective iteration. The agent stayed scoped, preserved the visual quality of the page, and resolved the manual-review UX issues without overengineering the solution. | This iteration worked well because the prompt was tightly constrained around two concrete review findings: input hardening and layout resilience. The combination of simple input sanitization and targeted CSS was enough to fix the visible problems quickly. The next important step is to align backend validation with the improved frontend behavior.
# Implementer Prompt - Iteration 07 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-07/00-iteration-brief.md - sistema/docs/iterations/iteration-07/01-planner-output.md - sistema/server/src/modules/students/student.validation.ts - sistema/server/src/modules/students/student.service.ts - sistema/server/src/modules/students/index.ts Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly and kept the rule centralized, but CPF validation is still intentionally basic. It now enforces numeric-only plus exact length 11, but it does not attempt richer CPF business validation beyond that scope. | Accepted | Good backend hardening iteration. The agent stayed narrowly scoped, changed only the right layer, and aligned backend validation with the frontend behavior without unnecessary refactoring. | This iteration worked well because the requirement was simple, explicit, and strongly constrained toward one shared validation point. The result improved system integrity by ensuring invalid CPF values can no longer bypass the frontend and enter through direct API calls.
# Implementer Prompt - Iteration 08 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-08/00-iteration-brief.md - sistema/docs/iterations/iteration-08/01-planner-output.md - sistema/client/src/pages/StudentsPage.tsx - sistema/client/src/config/studentsApi.ts - sistema/client/src/styles.css - sistema/client/src/types/domain.ts Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly and delivered edit mode cleanly, but the students page is becoming more feature-dense. The current shared form approach still works well, yet future iterations should keep guarding against excessive logic growth inside the page component. | Accepted | Good frontend iteration. The agent stayed scoped, preserved the current visual quality, and added edit mode without breaking the existing create flow. | This iteration worked well because the prompt explicitly required reuse of the existing form and strong visual edit-mode cues. That prevented unnecessary duplication and kept the page coherent. The next step should complete the students frontend flow with delete functionality.
# Implementer Prompt - Iteration 09 Before making any code changes, read and consider these files from the workspace: - sistema/.github/copilot-instructions.md - sistema/docs/project-scope.md - sistema/docs/iterations/iteration-09/00-iteration-brief.md - sistema/docs/iterations/iteration-09/01-planner-output.md - sistema/client/src/pages/StudentsPage.tsx - sistema/client/src/config/studentsApi.ts - sistema/client/src/styles.css - sistema/client/src/types/domain.ts Do not edit any file yet. First, respond only with: 1. Objective 2. Files you intend to change 3. Out of scope 4. Short implementation plan 5. Manual validation steps 6. Risks or caveats Wait for my approval before making changes. | The implementation behaved correctly and kept the delete flow well scoped, but the students page now carries create, edit, and delete behavior in one component. The current localized approach still works, yet future iterations should continue watching for excessive UI-state growth. | Accepted | Good frontend iteration. The agent preserved the current visual style, added delete cleanly, and kept the full students flow coherent without unnecessary complexity. | This iteration worked well because the prompt explicitly separated delete from confirmation-modal complexity and required correct interaction with edit mode. The result completed the core students frontend workflow while keeping the page visually consistent.